## Part I-Instuctions
Duke OSW ARFI Submission Uptake Form - Version FINAL 01/29/2025
Part I
Guidelines and Instructions
Duke Energy OSW ARFI Submission Uptake Form
Duke OSW ARFI Submission Uptake Form - Version FINAL 01/29/2025
Part I (continued)
Guidelines and Instructions
END
This Submission Uptake Form comprises Part I through Part VI as referenced in the Acquisition Request for Information (ARFI).
This Submission Uptake Form is password protected.
Writeable fields designed for Participant inputs can be unlocked with the password "ARFI".
Parts II through VI of this Attachment must be completed directly in this Excel spreadsheet and submitted according to the instructions in Part I and the remainder of the Submission Form. Please read these instructions in their entirety.
Submissions must include an approximate net generating capacity of 800-1,100 MW of offshore wind (OSW) with commercial operation (COD) by January 1, 2034 and may further include 2,200-2,400 MW by commercial operation by January 1, 2035, inclusive of all generation (± rounded up, to the next whole wind turbine generator) and transmission interconnection to a point of interconnection (POI) with the grid, owned and operated by either Duke Energy Carolinas, LLC (DEC) or Duke Energy Progress, LLC (DEP, and together with DEC, “Duke Energy” or equivalently “the Utilities”) and an hourly profile production schedule delivered to the on-shore interconnection point (POI).
The New Bern, North Carolina substation is the required POI for the Minimum Submission for this ARFI. Alternative POIs may be submitted. If submitting multiple proposals with different capacity sizes, commercial operation dates, on-shore interconnection points, or production schedules, please submit separate ARFI forms for each unique project submission and indicate the name of each ARFI form using the following filename format: [Participant Name]_["Minimum Submission"/"Alternate #"]_[POI Name]_[Project Name]_[#]MW_COD [mm/dd/yy].
E.g, OSWDeveloperX_Minimum Submission_NewBern_BestProjectEver_1100MW_2034.xlsx
Part II - Submission Certification and Authorization and Participant Contact Information
Proposal Certification, name of the bidder, project name, and contact info.
Part III - Submission Identification and Definitions
Part III requires the Participant to provide a summary of how this Submission meets the Definitions included in the ARFI.
Part IV - Eligible Facility Summary Information
Part IV provides technical information about a facility and facility parameters to be considered in the evaluation. If the Submission is for a one phase project, please complete Part IV(a). If the Submission includes more than one phases of development, Part IV (a) must be completed for the first phase, and Part IV (b) must be completed for the second phase, and so forth, respectively, as applicable.
Part V - Project Schedules, Cash Flows and Project Price Details
Part V relates to Project schedule, capital expenditures during construction, and Project Price.
In Part V (a) the Participant should enter the Commercial Operation Date and complete the table specifrying the timing of the Project Milestones. In addition, the Participant is requested to provide the estimated quarterly cash flows regardless of whether those align with specific Project Milestones or not. An brief summary of each quartely cash flow should be provided.
Part V (b)(i) requires the entry of the total Project Price, whether a single payment by the Utilities or a set of Progress Payments. Part V(b)(ii) requests details related to the milestones, timing and amount of any Progress Payment arrangement proposed for an Alternate Submission.
Part V (b)(iii) requires the total Project Price, or sum of Project Milestone payments, to be stated in terms of amounts associated with specific Project components such as turbine supply, cabling, insurance, and development fee.
Part VI - Operational Information (Expected Hourly, Monthly and Annual Production Data)
The forms are used to convey the information about the quantity and timing of energy to be delivered. The data entry must be provided in an 'hourly profile' format. Hourly Profile data is entered in Part VI(a)(i), and provides for greater modeling accuracy during the evaluation process. It is requested that the bidder provide hourly production data representative of a specific year (8,760 or 8,784 data points). Table Part VI (a) will be populated automatically from your data entered in Part VI(a)(i), creating the project's 12 x 24 annual energy production. Participants are required to provide an hourly profile based on the average or middle year of the 30 year asset life and assures consistency in evaluation of bids.
If the bid proposal is for a one-phase project, please provide data in tab Part VI (phase 1). If a proposal includes two (2) phases of development, you must provide separate data for each relevant phase, i.e., tabs 'Part VI (Phase 1)', and 'Part VI (Phase 2)', respectively. If your Submission requires more than two phases, please email the Independent Evaluator at dukeoswie@poweradvisoryllc.com.
Part VI (b) provides monthly adjustment factors for up to 30 years to adjust for varying maintenance assumptions and declining output. The factors are for specific months and years, so the factors should coincide with the expected COD. The values should be expressed in decimal format, where 1 means no change to the output. Any reductions should be reflect as 1 less the outage rate (i.e. a 1% decrease in output should be input as 0.99).
Part VI (c) provides annual adjustment factors to further adjust the output for facility ramp-up and unplanned outages.

## Part II-Certifications
Duke OSW ARFI Submission Uptake Form - Version FINAL 01/29/2025
Part II (a)
Submission Certification and Authorization Form
| Project File Name |  |  | Required Information
As Submitted to the ARFI Submission Portal, see Part I-Instructions
| Project Title(s) |  |  | Required Information
| Submitting Party's Name |  |  | Required Information
Submitting Party or
| Authorized Representative |  |  | Required Information
|  | Submitting Party Representative's Title |  |  | Date
Signature of Submitting Party or Authorized Representative
Duke OSW ARFI Submission Uptake Form - Version FINAL 01/29/2025
Part II (b)
Bidder and Contact Information
Contact Information For Project
| Name |  | Required Information
| Mailing Address |  | Required Information
Courier Address
(if different)
| Telephone Number |  | Required Information
| E-mail Address |  | Required Information
Alternate Contact (Optional)
Name
Mailing Address
Courier Address
(if different)
Telephone Number
E-mail Address
END
A Submission will be considered incomplete unless all required signatures are provided below.
The undersigned certifies that, as a Participant of this ARFI, he or she is an authorized officer or other authorized representative of the Wind Energy Area (WEA) Leaseholder, and further certifies that:
(1) the Participant has reviewed this ARFI and all attachments and has investigated and informed itself with respect to all matters pertinent to this ARFI and its Submission; (2) the Submission is in compliance with all applicable federal, state and local laws and regulations, including antitrust and anti-corruption laws; (3) the Submission is made independently and that it has no knowledge of non-public information associated with a Submission by another party in response to this ARFI other than a Submission: (a) by an affiliate of the Participant, or (b) for a project in which that bidder is also a project proponent or participant, which, in each case, must be disclosed in writing to the ARFI Evaluation Team with each such Submission; (4) the Participant has no knowledge of any confidential information associated with development or evaluation process of the ARFI, or the development of the Asset Acquisition Reference Price; (5) the Project has not been developed utilizing knowledge of any non-public information associated with the development of the ARFI; (6) the Participant has not obtained any confidential bidding-related information directly or indirectly from any of the Utilities, in preparation of its Submission; (7) except as disclosed by the Participant in the relevant portions of its response, the Participant is not an Affiliated Company of the Utilities which are seeking Submission pursuant to the ARFI, has a financial or voting interest, controlling or otherwise in the Participant or the submitted project; (8) the Participant accepts that confidential information about their proposal might be shared with any members of the ARFI Evaluation Team, including the Evaluation Team’s Technical Advisor, the Independent Evaluator; the Participant shall abide by/accept all rules and protocols put in place to maintain a fair, competitive, and transparent ARFI process; and (9) the bidder will continue to observe these requirements throughout the ARFI process. Violation of any of the above requirements may be reported to the appropriate government authorities and shall disqualify the Participant from the ARFI process.
The undersigned further certifies (1) that the prices, terms and conditions of the Submission are valid and shall remain open, without modification except as allowed in this ARFI, until July 30, 2025, unless otherwise extended by mutual agreement between the Participant and the Utilities issuing this ARFI; (2) that he or she has personally examined and is familiar with the information in this Submission and all appendices thereto, and based on reasonable investigation, including inquiry of the individuals responsible for obtaining the information, the submitted information is true, accurate and complete to the best of the undersigned’s knowledge and belief; and (3) the undersigned understands that a false statement or failure to disclose material information in the submitted proposal may be punishable as a criminal offense under applicable law. The undersigned further certifies that that this proposal is on complete and accurate forms as provided without alteration of the text. The undersigned further understands and agrees to comply with all of the provisions of this ARFI, including those related to dispute resolution and handling of confidential information, and consents to the limited exchange and sharing of confidential information related to the Bidder’s proposal as described in this ARFI, including with members of the ARFI Evaluation Team, including the Evaluation Team’s Technical Advisor, the Independent Evaluator.

## Part III-Submission ID
Duke OSW ARFI Submission Uptake Form - Version FINAL 01/29/2025
Part III
Submission Identification and Definitions
| Submitting Party's Name | Required Information
| Project Title | Required Information
Provide a summary description of the following:
How this proposal meets the definition of "Offshore Wind Energy Generation"
Required Information
How the developer of this Submission meets the definition of "Offshore Wind Developer"
Required Information
How this proposal contributes to reducing Winter and/or Morning Electricity Price Spikes
Required Information
END

## Part IV(a-c) - SiteProject Desc
Duke OSW ARFI Submission Uptake Form - Version FINAL 01/29/2025
Part IV (a), (b), & (c)
Site Project Description (Conditions, Project Design Elements, & Logistics and Vessel Plan)
Part IV (a)
Site Conditions
Required Inputs
|  | Water depth range within the Project envelope | Min |  |  | meters
|  |  | Max |  |  | meters
|  | Mean water depth at proposed turbine locations |  |  |  | meters
|  | Mean air density |  |  |  | kg/m3
|  | Long-term average wind speed by month at hub height | Jan |  |  | meters/sec
|  |  | Feb |  |  | meters/sec
|  |  | Mar |  |  | meters/sec
|  |  | Apr |  |  | meters/sec
|  |  | May |  |  | meters/sec
|  |  | Jun |  |  | meters/sec
|  |  | Jul |  |  | meters/sec
|  |  | Aug |  |  | meters/sec
|  |  | Sep |  |  | meters/sec
|  |  | Oct |  |  | meters/sec
|  |  | Nov |  |  | meters/sec
|  |  | Dec |  |  | meters/sec
|  | Extreme wind speed at hub height | Return period (years)
|  |  | 1 |  | 10 | 50 | 100
10 min
1 min
3 sec gust
|  | Waves | Return period (years)
|  |  | 1 |  | 10 | 50 | 100
Maximum individual wave height (m)
Associated period (s)
Significant wave height (m)
|  | Sea temperature | Lowest |  |  | degrees C
|  |  | Highest |  |  | degrees C
|  | Measurement Methodology | Response
On-site wind resource measurement device
On-site wind resource measurement duration
On-site wind resource measurement data capture percentage
Long term wind resource measurement reference used to extend on-site data
Long term wind resource measurement reference data period
Correlation coefficient between on-site data and long-term reference
Continued below
Duke OSW ARFI Submission Uptake Form - Version FINAL 01/29/2025
Part IV (b)
Project Design Elements
Required Inputs
|  | Turbine Concept |  | Capacity (MW) | Value | Units | Notes
Turbine Supplier
|  | Turbine Model Capacity |  |  |  | MW
|  | Hub height |  |  |  | m
|  | Rotor diameter |  |  |  | m
|  | Rated wind speed |  |  |  | m/s
|  | Cut-in wind speed |  |  |  | m/s
|  | Cut-out wind speed |  |  |  | m/s
|  | Substructure Concept |  | Capacity (MW) | Value | Units | Notes
Turbine Substructure Design (e.g., monopile with Transition Piece)
Turbine Substructure Supplier
|  | Mass of substructure |  |  |  | mt
|  | Mass of Transition Piece (if required) |  |  |  | mt
|  | Diameter at seabed |  |  |  | m
|  | Average overall length |  |  |  | m
|  | Average embedment depth |  |  |  | m
|  | Inter-Array Cable Concept |  | Capacity (MW) | Value | Units | Notes
Inter-Array Cable Supplier
|  | Inter-Array Cable Voltage |  |  |  | kV
Number of strings
|  | Inter-Array Cable Total Distance |  |  |  | m
|  | Offshore Substation / Converter Station Concept |  | Capacity (MW) | Value | Units | Notes
Offshore Substation Topside Supplier
Offshore Substation Foundation Supplier
|  | Offshore Substation Total Transfomer arrangement and capacity |  |  |  | MW
Offshore Substation HVAC or HVDC?
|  | Topside dimensions (length x width x height) |  |  |  | m x m x m
Offshore Substation Foundation Concept (i.e. 4 leg jacket, 3 leg jacket, monopile)
|  | Mass of Foundation |  |  |  | mt
|  | Dimensions of Foundation at seabed |  |  |  | m x m
|  | Export Cable Concept |  | Capacity (MW) | Value | Units | Notes
Offshore Export Cable Supplier
|  | Offshore Export Cable Voltage |  |  |  | kV
Number of circuits
|  | Offshore Export Cable Total Distance |  |  |  | m
Offshore Export Cable monopole or bipole? (HVDC)
|  | Layout |  | Capacity (MW) | Value | Units | Notes
Number of Turbine Positions
Number of Offshore Substations
|  | Grid Spacing |  |  |  | m x m
|  | Onshore Design Concepts |  | Capacity (MW) | Value | Units | Notes
|  | Shore Landing Location Coordinates |  |  |  | °N x °W
Landfall Design (i.e. two underground transition vaults)
|  | Landfall Design Area Requirements |  |  |  | m x m
Onshore Export Cable Supplier
|  | Onshore Export Cable Voltage |  |  |  | kV
Number of circuits
|  | Onshore Export Cable Total Distance |  |  |  | m
Onshore Export Cable monopole or bipole? (HVDC)
New onshore substation part of proposal? (yes/no)
Onshore Substation Total Transformer arrangement and capacity
Point of Interconnection (If Minimum Qualifying Submission, POI must be New Bern)
Continued below
Duke OSW ARFI Submission Uptake Form - Version FINAL 01/29/2025
Part IV (c)
Logistics and Vessel Plan
Required Inputs
Construction
Anticipated staging port name and location
Port lease in place? (yes/no)
Port upgrades required? (yes/no)
Additional staging locations for major components
Turbine installation vessel anticipated
Turbine installation vessel contracted (yes/no)
Monopile installation vessel anticipated
Monopile installation vessel contracted (yes/no)
Substation installation vessel anticipated
Substation installation vessel contracted (yes/no)
Cable lay vessel anticipated
Cable lay vessel contracted (yes/no)
Operational Period
Anticipated primary O&M port
Primary O&M vessel type (i.e. CTV, SOV)
Number of primary O&M vessels
Primary O&M vessel new build? (yes/no)
Primary O&M vessel shared (yes/no)
END
This Project Site Conditions Form is a portion of the requirements of Section 8.B.i of the Acquisition Request for Information (ARFI). These minimum data requirements must be completed in the Excel spreadsheet below and submitted in addition to any required narrative outlined in the above referenced Section of the ARFI.
This Project Design Elements Form is a portion of the requirements of Sections 8.B.ii, 8.B.iv, and 8.B.v of the Acquisition Request for Information (ARFI). These minimum data requirements must be completed in the Excel spreadsheet below and submitted in addition to any required narrative outlined in the above referenced Sections of the ARFI. Additional notes pertaining to the individual entries should be provided where needed in the space adjacent to the input description. This Form assumes that data is consistent for the Project, regardless of the number of phases. If this is not consistent with your Submission, please email the Independent Evaluator at dukeoswie@poweradvisoryllc.com
The Logistics Form is a portion of the requirements of Section 8.B.iii and vi of the Acquisition Request for Information (ARFI). This Logistics Form must be completed in the Excel spreadsheet below and submitted in addition to any required narrative outlined in the above referenced Sections of the ARFI. Please read these instructions in their entirety.
The following parts of the Submission Form pertain to the Site Conditions - Part IV (a), Project Design Elements - Part IV (b), and Logistics and Vessel Plan - Part IV (c). Please read the instructions pertaining to each Part below and its corresponding description in Part I - Guidelines and Instructions of this Submission Form in their entirity before completion of the below information. The following Forms assume that data is consistent for the Project, regardless of the number of phases. If this is not consistent with your Submission, please email the Independent Evaluator at dukeoswie@poweradvisoryllc.com.

## Part IV(d) - Project Schedule
Duke OSW ARFI Submission Uptake Form - Version FINAL 01/29/2025
Part IV (d)
Project Schedule
|  |  | Phase 1 - Required |  | Phase 2 - Optional
| Category | Milestones | Capacity (MW) | Proposed Date (MM/YYYY) | Capacity (MW) | Proposed Date (MM/YYYY)
| Permitting | SAP Submitted
SAP Approved
Submission of COP
Draft Environmental Impact Statement (EIS)
Final EIS
BOEM COP Approval
BOEM Record of Decision (ROD)
FDR/FIR Approval
All state permits received
All local approvals received
MORE DETAILED REQUESTS
Environmental Protection Agency (Air Permit)
National Historic Preservation Act (NHPA)
US Army Corp of Engineers (CWA/RHA)
National Marine Fisheries Service (LOA/ITA)
FAA determination of No Hazard
Federal Consistency Review(s) Issued
Duke OSW ARFI Submission Uptake Form - Version FINAL 01/29/2025
|  |  | Phase 1 - Required |  | Phase 2 - Optional
| Category | Milestones | Capacity (MW) | Proposed Date (MM/YYYY) | Capacity (MW) | Proposed Date (MM/YYYY)
| Major components (offshore) | Offshore substation foundation supply contract executed
Offshore substation foundation fabrication start
Offshore substation foundation fabrication end
Offshore substation foundation installation start
Offshore substation fouundation installation end
Offshore substation topside supply contract executed
Offshore substation topside fabrication start
Offshore substation topside fabrication end
Offshore substation topside installation start
Offshore substation topside installation end
Offshore substation testing and commissioning completion
Offshore substation energization
Monopile supply contract executed
Monopile fabrication start
Monopile fabrication end
Monopile installation start
Monopile installation end
Transition piece supply contract executed
Transition piece fabrication start
Transition piece fabrication end
Transition piece installation start
Transition piece installation end
Turbine supply contract executed
Turbine model certification achieved
Turbine fabrication start
Turbine fabrication end
Turbine installation start
Turbine installation end
Turbine hot commissioning completion
Inter-array cable supply contract executed
Inter-array cable fabrication start
Inter-array cable fabrication end
Inter-array cable installation start
Inter-array cable installation end
Inter-array cable termination completion
Export cable supply contract executed
Export cable fabrication start
Export cable fabrication end
Export cable installation start
Export cable installation end
Export cable termination completion
Export cable energization
Duke OSW ARFI Submission Uptake Form - Version FINAL 01/29/2025
|  |  | Phase 1 - Required |  | Phase 2 - Optional
| Category | Milestones | Capacity (MW) | Proposed Date (MM/YYYY) | Capacity (MW) | Proposed Date (MM/YYYY)
| Major components (onshore) | Landfall / HDD civil works start
Landfall / HDD civil works completion
Onshore export cable fabrication start
Onshore export cable fabrication end
Onshore export cable installation start
Onshore export cable installation end
Onshore export cable termination completion
Onshore export cable energization
Substation civil works start
Substation civil works end
Substation mechanical and electrical completion
Substation site acceptance testing (pre-energization)
Substation energization
| Category | Milestones | Capacity (MW) | Proposed Date (MM/YYYY) | Capacity (MW) | Proposed Date (MM/YYYY)
| Port(s) and vessels | Construction port lease commencement
Turbine installation vessel contract execution
Turbine installation vessel charter period start
Turbine installation vessel charter period end
Monopile installatin vessel contract execution
Monopile installation vessel charter period start
Monopile installation vessel charter period end
Primary O&M vessel contract execution
| Category | Milestones | Capacity (MW) | Proposed Date (MM/YYYY) | Capacity (MW) | Proposed Date (MM/YYYY)
| Project completion | Project mechanical completion
Project substantial completion
Grid connection testing complete
Turbine first power
Commerical Operations Date
Placed in Service
| Category | Milestones | Capacity (MW) | Proposed Date (MM/YYYY) | Capacity (MW) | Proposed Date (MM/YYYY)
| Operational | O&M port lease commencement
Onshore O&M facilities work start
Onshore O&M facilities work end
Decommissioning Initiated
Decommissioning completed
END
This Project Schedule Form is a portion of the requirements of Section 8.B.xiv of the Acquisition Request for Information (ARFI). This Project Schedule form must be completed in this Excel spreadsheet and submitted according to the instructions Part I - Guidelines and Instructions of this Submission Form in their entirity before completion of the below information. Please read these instructions in their entirety. If the Project is completed in two (2) phases, Optional fields have been provided. If the Project requires more than two (2) Phases, please email the Independent Evaluator at dukeoswie@poweradvisoryllc.com.

## Part IV(e) - O&M Proposal
Duke OSW ARFI Submission Uptake Form - Version FINAL 01/29/2025
Part IV (e)
Operations and Maintenance Cost
Phase 1 - Required
| Operations Year | Capacity (MW) | Marine Logistics | O&M Facilties and On-Shore Equipment | Routine Maintenance | Equipment Replacement | Maintenance / Replacement Reserves | Lease Fees | Environmental and Stakeholder Costs | Legal and Administrative | OTHER - Please Specify | Total Operations and Maintenance
| 1 | [10 empty] | 0
| 2 | [10 empty] | 0
| 3 | [10 empty] | 0
| 4 | [10 empty] | 0
| 5 | [10 empty] | 0
| 6 | [10 empty] | 0
| 7 | [10 empty] | 0
| 8 | [10 empty] | 0
| 9 | [10 empty] | 0
| 10 | [10 empty] | 0
| 11 | [10 empty] | 0
| 12 | [10 empty] | 0
| 13 | [10 empty] | 0
| 14 | [10 empty] | 0
| 15 | [10 empty] | 0
| 16 | [10 empty] | 0
| 17 | [10 empty] | 0
| 18 | [10 empty] | 0
| 19 | [10 empty] | 0
| 20 | [10 empty] | 0
| 21 | [10 empty] | 0
| 22 | [10 empty] | 0
| 23 | [10 empty] | 0
| 24 | [10 empty] | 0
| 25 | [10 empty] | 0
| 26 | [10 empty] | 0
| 27 | [10 empty] | 0
| 28 | [10 empty] | 0
| 29 | [10 empty] | 0
| 30 | [10 empty] | 0
Duke OSW ARFI Submission Uptake Form - Version FINAL 01/29/2025
Part IV (e)
Operations and Maintenance Cost
Phase 2 - Optional
| Operations Year | Capacity (MW) | Marine Logistics | O&M Facilties and On-Shore Equipment | Routine Maintenance | Equipment Replacement | Maintenance / Replacement Reserves | Lease Fees | Environmental and Stakeholder Costs | Legal and Administrative | OTHER - Please Specify | Total Operations and Maintenance
| 1 | [10 empty] | 0
| 2 | [10 empty] | 0
| 3 | [10 empty] | 0
| 4 | [10 empty] | 0
| 5 | [10 empty] | 0
| 6 | [10 empty] | 0
| 7 | [10 empty] | 0
| 8 | [10 empty] | 0
| 9 | [10 empty] | 0
| 10 | [10 empty] | 0
| 11 | [10 empty] | 0
| 12 | [10 empty] | 0
| 13 | [10 empty] | 0
| 14 | [10 empty] | 0
| 15 | [10 empty] | 0
| 16 | [10 empty] | 0
| 17 | [10 empty] | 0
| 18 | [10 empty] | 0
| 19 | [10 empty] | 0
| 20 | [10 empty] | 0
| 21 | [10 empty] | 0
| 22 | [10 empty] | 0
| 23 | [10 empty] | 0
| 24 | [10 empty] | 0
| 25 | [10 empty] | 0
| 26 | [10 empty] | 0
| 27 | [10 empty] | 0
| 28 | [10 empty] | 0
| 29 | [10 empty] | 0
| 30 | [10 empty] | 0
END
The Project O&M Proposal Form is a portion of the requirements of Section 8.C of the Acquisition Request for Information (ARFI). This form should be used for both the Minimum Submission Requirements of a 10-year O&M cost estimate (Section 8.C.iii of the ARFI) as well as for Submissions including an SLA (Section 8.C.vi of the ARFI). All values should be stated in base year 2025 $US. This Form includes two O&M cost-estimate schedules in the case that the Project is being delivered in two (2) phases. Completion of the uppermost table is required, while the lower table is optional, to be completed, as relevant, to accurately reflect the Submission. If the Project requires more than two (2) Phases, please email the Independent Evaluator at dukeoswie@poweradvisoryllc.com.

## Part IV(f) - Decommissioning
Duke OSW ARFI Submission Uptake Form - Version FINAL 01/29/2025
Part IV (f)
Decomissioning Costs
Required Inputs
Decommissioning start date
Decommissioning end date
| 0 | Total cost to remove Project infrastructure according to US Code of Federal Regulations, Part 585
Removal of turbines and towers
Removal of foundations and substructures
Removal of inter-array cabling and transformation
Removal of offshore substation
Removal of export cabling
Miscellaneous removal costs
END
The Decommissioning Form is a portion of the requirements of Sections 8.D of the Acquisition Request for Information (ARFI). These minimum data requirements must be completed in the Excel spreadsheet below and submitted in addition to any required narrative outlined in the above referenced Sections of the ARFI. The total cost to remove the project should represent the full cost of removal, salvage and disposal of the Project assets at the end of its design life including transportation and labor. All costs should be stated in base year 2025 $US. The following Form assumes that data is consistent for the Project, regardless of the number of phases. If this is not consistent with your Submission, please email the Independent Evaluator at dukeoswie@poweradvisoryllc.com.

## Part V(a)&(b) - CashFlow & Pmts
Duke OSW ARFI Submission Uptake Form - Version FINAL 01/29/2025
| Part V (a) and (b)(i-iii) | [5 empty] | Part V (b)
| Project Cash Flows and Milestone Payments | [5 empty] | Project Pricing
Part V(b)(i)
Total Project Price to Utilities - Lump Sum (Single Payment)
[7 empty] | 0 |  |  | For Minimum Qualifying Submission, Single Payment of Total Project Price Upon Placed in Service (Required)
| Part V (a) | [5 empty] | Part V(b) (ii) |  |  |  |  | Part V(b) (iii)
| Commercial Operations | Year | Quarter | Capacity (MW) |  |  | Total Project Price to Utilities - Payment Milestones |  |  |  |  | Total Project Price to Utilities - Price Price Components
| Phase 1 |  |  |  | Required Fields
| Phase 2 |  |  |  | Note: Outermost date targeted under this ARFI (Q4, 2035)
|  |  | Required Fields | [5 empty] | Required Fields
| Time Period | [5 empty] | Time Period |  |  |  | Percentage (%) |  | Required Fields
| Year | Quarter | Project Milestone |  | Cash Flow ($) | Cash Flow Explanation | Year | Quarter | Payment Milestones | Amount ($) |  | Project Price Detail | Amount ($) | Notes
| 2035 | 3 |  |  |  |  | 2035 | 3 |  |  |  | Development Expenses
| 2035 | 2 |  |  |  |  | 2035 | 2 |  |  |  | Turbine Supply
| 2035 | 1 |  |  |  |  | 2035 | 1 |  |  |  | Turbine Transport and Installation (T&I)
| 2034 | 4 |  |  |  |  | 2034 | 4 |  |  |  | Monopile Design and Fabrication
| 2034 | 3 |  |  |  |  | 2034 | 3 |  |  |  | Transition Piece (TP) Design and Fabrication
| 2034 | 2 |  |  |  |  | 2034 | 2 |  |  |  | Monopile and TP T&I
| 2034 | 1 |  |  |  |  | 2034 | 1 |  |  |  | Inter-array cabling and installation
| 2033 | 4 |  |  |  |  | 2033 | 4 |  |  |  | Export cabling and installation
| 2033 | 3 |  |  |  |  | 2033 | 3 |  |  |  | Onshore Cabling and Installation
| 2033 | 2 |  |  |  |  | 2033 | 2 |  |  |  | Shore Landing Civil Work
| 2033 | 1 |  |  |  |  | 2033 | 1 |  |  |  | Onshore Substation and Installation
| 2032 | 4 |  |  |  |  | 2032 | 4 |  |  |  | Onshore O&M Facilities
| 2032 | 3 |  |  |  |  | 2032 | 3 |  |  |  | Interconnection and HVDC Cabling
| 2032 | 2 |  |  |  |  | 2032 | 2 |  |  |  | Construction Management and Permitting/Compliance
| 2032 | 1 |  |  |  |  | 2032 | 1 |  |  |  | Contingency and Risk
| 2031 | 4 |  |  |  |  | 2031 | 4 |  |  |  | Insurance
| 2031 | 3 |  |  |  |  | 2031 | 3 |  |  |  | Development Fee
| 2031 | 2 |  |  |  |  | 2031 | 2 |  |  |  | Margin
| 2031 | 1 |  |  |  |  | 2031 | 1 |  |  |  | Construction Financing
| 2030 | 4 |  |  |  |  | 2030 | 4 |  |  |  | Other |  | (Please replace title and explain in Notes)
| 2030 | 3 |  |  |  |  | 2030 | 3
| 2030 | 2 |  |  |  |  | 2030 | 2
| 2030 | 1 |  |  |  |  | 2030 | 1
| 2029 | 4 |  |  |  |  | 2029 | 4
| 2029 | 3 |  |  |  |  | 2029 | 3
| 2029 | 2 |  |  |  |  | 2029 | 2
| 2029 | 1 |  |  |  |  | 2029 | 1
| 2028 | 4 |  |  |  |  | 2028 | 4
| 2028 | 3 |  |  |  |  | 2028 | 3
| 2028 | 2 |  |  |  |  | 2028 | 2
| 2028 | 1 |  |  |  |  | 2028 | 1
| 2027 | 4 |  |  |  |  | 2027 | 4
| 2027 | 3 |  |  |  |  | 2027 | 3
| 2027 | 2 |  |  |  |  | 2027 | 2
| 2027 | 1 |  |  |  |  | 2027 | 1
| 2026 | 4 |  |  |  |  | 2026 | 4
| 2026 | 3 |  |  |  |  | 2026 | 3
| 2026 | 2 |  |  |  |  | 2026 | 2
| 2026 | 1 |  |  |  |  | 2026 | 1
| 2025 | 4 |  |  |  |  | 2025 | 4
| 2025 | 3 |  |  |  |  | 2025 | 3
| 2025 | 2 |  |  |  |  | 2025 | 2
| 2025 | 1 |  |  |  |  | 2025 | 1
| 2024 | 4 |  |  |  |  | 2024 | 4
| 2024 | 3 |  |  |  | (Include all prior expenses) | 2024 | 3
|  |  |  | TOTAL EXPENDITURES | 0 |  |  |  | TOTAL PROJECT PRICE | 0 | 0% | PROJECT PRICE DETAIL | 0
[7 empty] | Must equal sum of Project Price Detail (Cell O83 must equal Cell U83) |  |  | OK | Not 100%
END
This Project Cash Flow Form is a portion of the requirements of Section 8.E. of the Acquisition Request for Information (ARFI). This Project CashFlow form must be completed in this Excel spreadsheet and submitted according to the instructions in the applicable Section(s) of the ARFI. Please read these instructions in their entirety.
At a minimum, Participant must include entries in the "Project Milestone" column below associated with the following key project milestones:
- Build-Own-Transfer (BOT) Contract Execution
- Supply Contract Executed
- FDR/FIR Approval
- Monopile Install Complete
- Turbine Install Complete
- Offshore SubStation Energized
- Onshore Substation Energized
- Project Substantial Completion
- Commerical Operations
If no material Project Cash Flows align with one or more of these key project milestones, no Project Cash Flow entry is required for that item. However, Participant must include amounts and timing of all major project capital outflows under Project Cash Flow as well as a brief explanation of those expenditures. The total of all Project Cash Flows should represent the total cost of the Project to the Participant and does not necessarily equal the Project Price.
If the Project is developed in phases, please specify the phase associated with each Milestone. For example, if the Project consists of two phases, there should be separate Phase 1 and Phase 2 (or more) entered for each of the above milestones (e.g., "Phase 1 - Monopile Install Complete").
This Project Pricing Form is a portion of the requirements of Section 8.F.i of the Acquisition Request for Information (ARFI). This Form must be completed in this Excel spreadsheet and submitted according to the instructions in the applicable Section(s) of the ARFI. Please read these instructions in their entirety.
For Minimum Qualifying Submission, Participant must provide a single payment Total Project Price to be paid by the Utilities upon the Project achieving Placed in Service in Part V(b)(i). Alternative payment structures may be proposed for Alternative Submissions. Any payment arrangments based upon project milestones should be entered into the space provided Part V(b)(ii), below.
Participant must include amounts that total to the Total Project Price in Part V(b)(i), as applicable, for both the Payment Milestones in Part V(b)(ii) and Project Price Components in Part V(b)(iii) that represent the total cost to the Utilities associated with the development, construction and transfer of the Project.
In the event the Project is developed in phases, information provided in Part V(b)(ii) should be provided separately for each phase and specified as such, as described in the instructions for Part V(a) (left). For a phased Project, information in the "Notes" section of Part V(b)(iii) should specify the allocation of the corresponding value in the "Amount ($)" column associated with each phase. Additionally, the Total Project Price value at the bottom of Part V(b)(ii) must equal the Project Price Detail value at the bottom of Part V(b)(iii).

## Part VI - Prod Data (Phase 1)
| Duke OSW ARFI Submission Uptake Form - Version FINAL 01/29/2025 | [13 empty] | Duke OSW ARFI Submission Uptake Form - Version FINAL 01/29/2025 | [11 empty] | Hourly Profile |  |  |  |  | Duke OSW ARFI Submission Uptake Form - Version FINAL 01/29/2025
| Part VI | [13 empty] | Part VI (a) | [16 empty] | Part VI (a) (i)
| Prodution Data | [13 empty] | Operational Information - Production Data of Offshore Wind Project | [16 empty] | Representative Deliveries in Representative Year
[15 empty] | Hourly Delivery in MW (Averaged) - 12 Months by 24 Hours For Representative Day For Each Month | [17 empty] | Enter data for a single year representative of the Project's 30-year average production
Projects must provide 8,760 hourly energy production data. From the hourly energy production data, the 30-year average in MW, inclusive of wake losses, suboptimal performance, environmental losses and electrical losses will be calculated automatically and will populate Part VI(a). For the avoidance of doubt, hourly production values should represent energy delivered to the POI assuming 100% turbine and balance of plant availability.
You must insert an Hourly Profile, do so to the right by completing VI(a)(i). Table Part VI (a) below will be populated automatically from your data entered in Part V(a)(i), creating the project's 12 x 24 annual energy production inclusive of wake losses, suboptimal performance, environmental losses, and electrical losses. Downtime associated with O&M including planned or unplanned maintenance is not included and will be covered by Part VI (b) and Part VI (c) below.
|  | Legend | [31 empty] | Check: | 8,760 Hourly Values Missing
|  |  | Grey cell is automatically calculated | [27 empty] | Table VI(a) is incomplete, please enter all hourly profiles in VI (a) (i) >>> | JANUARY
White cell is to be updated by the WEA Leaseholder
|  | 0 | If sheet is filled out correctly, value to the immediate left should be zero | [29 empty] | HE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | Month
|  |  | Pre-populated | [12 empty] | HE | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 0 | [35 empty] | Avg | 0
1 | bar: HE to Dec
|  | Complete the fields below | [13 empty] | HE: 2 |  |  |  |  | 2
|  | Eligible Facility Location |  | Latitude | [11 empty] | HE: 3 |  |  |  |  | 3
|  |  |  | Longitude | [11 empty] | HE: 4 |  |  |  |  | 4
|  | Turbine capacity |  | MW | [11 empty] | HE: 5 |  |  |  |  | 5
|  | Number of turbines |  | # | [11 empty] | HE: 6 |  |  |  |  | 6
|  | Hub height |  | m | [11 empty] | HE: 7 |  |  |  |  | 7
[16 empty] | HE: 8 |  |  |  |  | 8
|  | Annual average wind speed at hub height across turbine locations | [13 empty] | HE: 9 |  |  |  |  | 9
|  |  |  | m/s | [11 empty] | HE: 10 |  |  |  |  | 10
[16 empty] | HE: 11 |  |  |  |  | 11
|  | Gross energy (annual 30-year average) | #DIV/0! | MWh/year | [11 empty] | HE: 12 |  |  |  |  | 12
[16 empty] | HE: 13 |  |  |  |  | 13
|  | Annual average losses | [13 empty] | HE: 14 |  |  |  |  | 14
|  | Internal wake losses | #DIV/0! | [12 empty] | HE: 15 |  |  |  |  | 15
|  | External wake losses | #DIV/0! | [12 empty] | HE: 16 |  |  |  |  | 16
|  | Suboptimal performance losses | #DIV/0! | [12 empty] | HE: 17 |  |  |  |  | 17
|  | Environmental losses | #DIV/0! | [12 empty] | HE: 18 |  |  |  |  | 18
|  | Electrical losses to POI | #DIV/0! | [12 empty] | HE: 19 |  |  |  |  | 19
|  | Project downtime - planned | #DIV/0! | [12 empty] | HE: 20 |  |  |  |  | 20
|  | Turbine downtime - unplanned | 100% | [12 empty] | HE: 21 |  |  |  |  | 21
|  | Balance of plant downtime - unplanned | 100% | [12 empty] | HE: 22 |  |  |  |  | 22
[16 empty] | HE: 23 |  |  |  |  | 23
|  | P50 Net energy (annual 30-year average) | #DIV/0! | MWh/year | [11 empty] | HE: 24 |  |  |  |  | 24
|  | P50 Net capacity factor | #DIV/0!
|  | 1-year P99 Net energy |  | GWh/year
1-year P99 Net capacity factor
[15 empty] | Duke OSW ARFI Submission Uptake Form - Version FINAL 01/29/2025 | [16 empty] | FEBRUARY
|  | Column ID | (i) | (ii) | (iii) | (iv) | (v) | (vi) | (vii) | (viii) | (ix) | (x) | (xi) |  | Part VI (b)
|  |  | Gross annual energy (MWh) | Internal wake loss (%) | External wake loss (%) | Suboptimal performance loss (%) | Environmental loss (%) | Electrical losses (%) | Gross Annual Energy minus (i)-(vi) losses (MWh) | Project downtime - planned (%) | Turbine downtime - unplanned (%) | Balance of plant downtime - unplanned (%) | Net annual energy (MWh) |  | Operational Information - PLANNED Maintenance Profile | [17 empty] | HE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 |  |  | Month
|  | P50 Annual Estimates | [12 empty] | Monthly Adjustment Factors as Percentage of Expected Production | [49 empty] | Avg
|  | Year | [30 empty] | 1
|  | 1 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | HE: Table VI(b) and VI(c) request information related to the maintenance requirements of the Project. There are two tables. The first, VI (b), requests the maintenance profile for PLANNED activities associated with both the turbines and all balance of plant. This would include all pre-scheduled maintence, inspections, tests, component and consumables replacement. VI( c) (below) requests the annual expectations for UNPLANNED activities for both the turbines and all balance of plant. The downtime estimates year to year are expected to be derived based on the experience of the developer and experience with the proposed technology. |  |  |  |  | 2
|  | 2 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! | [19 empty] | 3
|  | 3 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! | [19 empty] | 4
|  | 4 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! | [19 empty] | 5
|  | 5 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! | [19 empty] | 6
|  | 6 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! | [19 empty] | 7
|  | 7 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! | [19 empty] | 8
|  | 8 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! | [19 empty] | 9
|  | 9 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! | [19 empty] | 10
|  | 10 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | HE: Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) |  |  |  |  | 11
|  | 11 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Year | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  |  |  | 12
|  | 12 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! | [19 empty] | 13 | bar: Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year
|  | 13 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 2 |  |  |  |  | 14
|  | 14 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 3 |  |  |  |  | 15
|  | 15 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 4 |  |  |  |  | 16
|  | 16 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 5 |  |  |  |  | 17
|  | 17 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 6 |  |  |  |  | 18
|  | 18 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 7 |  |  |  |  | 19
|  | 19 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 8 |  |  |  |  | 20
|  | 20 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 9 |  |  |  |  | 21
|  | 21 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 10 |  |  |  |  | 22
|  | 22 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 11 |  |  |  |  | 23
|  | 23 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 12 |  |  |  |  | 24
|  | 24 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 13
|  | 25 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 14
|  | 26 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 15
|  | 27 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 16 |  |  |  | MARCH
|  | 28 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 17
|  | 29 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 18 |  |  |  |  | HE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | Month
|  | 30 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 19 | [36 empty] | Avg
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 20 |  |  |  |  | 1
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 21 |  |  |  |  | 2
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 22 |  |  |  |  | 3
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 23 |  |  |  |  | 4
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 24 |  | Table is Incomplete. Information may be Required. <<< |  |  | 5
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 25 |  |  |  |  | 6
Continued Right >>>> | [15 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 26 |  |  |  |  | 7
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 27 |  |  |  |  | 8
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 28 |  |  |  |  | 9
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 29 |  |  |  |  | 10
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 30 | 0 |  |  |  | 11
12
13
14
[15 empty] | Duke OSW ARFI Submission Uptake Form - Version FINAL 01/29/2025 | [17 empty] | 15
[15 empty] | Part VI (c) | [17 empty] | 16
[15 empty] | UNPLANNED Maintenance - Production Adjustment Assumptions | [17 empty] | 17
18
19
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) |  |  |  |  | 20
21
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: Year; Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Jan: Turbine ramp up downtime; Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Feb: Balance of plant ramp up downtime; Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Mar: Turbine downtime - all other; Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Apr: Balance of plant downtime - all other |  |  |  |  | 22
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: Year |  |  |  |  | 23
24 | bar: Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year
2
3
4
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 5 |  |  |  | APRIL
6
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 7 |  |  |  |  | HE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  | Month
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 8 | [36 empty] | Avg
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 9 |  |  |  |  | 1
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 10 |  |  |  |  | 2
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 11 |  |  |  |  | 3
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 12 |  |  |  |  | 4
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 13 |  |  |  |  | 5
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 14 |  |  |  |  | 6
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 15 |  |  |  |  | 7
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 16 |  |  |  |  | 8
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 17 |  |  |  |  | 9
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 18 |  |  |  |  | 10
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 19 |  |  |  |  | 11
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 20 |  |  |  |  | 12
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 21 |  |  |  |  | 13
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 22 |  |  |  |  | 14
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 23 |  |  |  |  | 15
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 24 |  | Table is Incomplete. Information may be Required. <<< |  |  | 16
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 25 |  |  |  |  | 17
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 26 |  |  |  |  | 18
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 27 |  |  |  |  | 19
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 28 |  |  |  |  | 20
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 29 |  |  |  |  | 21
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 30 | 0 |  |  |  | 22
23
24
Continued Right >>>>
MAY
[33 empty] | HE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | Month
Avg
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
JUNE
[33 empty] | HE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  | Month
Avg
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
JULY
[33 empty] | HE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | Month
Avg
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
AUGUST
[33 empty] | HE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | Month
Avg
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
SEPTEMBER
[33 empty] | HE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  | Month
Avg
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
OCTOBER
[33 empty] | HE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | Month
Avg
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
NOVEMBER
[33 empty] | HE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  | Month
Avg
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
DECEMBER
[33 empty] | HE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | Month
Avg
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
END
This Production Date Form is a portion of the requirements of Sections 8.B.vii of the Acquisition Request for Information (ARFI). These minimum data requirements must be completed in this Form and submitted in addition to any required narrative outlined in the above referenced Sections of the ARFI. Following the legend below, please complete the fields directly below and tables in Part VI (a) (i): Representative Deliveries in Representative Year (far right), and Part VI (b) and Part VI (c): Operational Data Adjustments for Planned and Unplanned Maintenance, respectively, in the center of this Form.

## Part VI - Prod Data (Phase 2)
| Duke OSW ARFI Submission Uptake Form - Version FINAL 01/29/2025 | [13 empty] | Duke OSW ARFI Submission Uptake Form - Version FINAL 01/29/2025 | [11 empty] | Hourly Profile |  |  |  |  | Duke OSW ARFI Submission Uptake Form - Version FINAL 01/29/2025
| Part VI | [13 empty] | Part VI (a) | [16 empty] | Part VI (a) (i)
| Prodution Data | [13 empty] | Operational Information - Production Data of Offshore Wind Project | [16 empty] | Representative Deliveries in Representative Year
[15 empty] | Hourly Delivery in MW (Averaged) - 12 Months by 24 Hours For Representative Day For Each Month | [17 empty] | Enter data for a single year representative of the Project's 30-year average production
Projects must provide 8,760 hourly energy production data. From the hourly energy production data, the 30-year average in MW, inclusive of wake losses, suboptimal performance, environmental losses and electrical losses will be calculated automatically and will populate Part VI(a). For the avoidance of doubt, hourly production values should represent energy delivered to the POI assuming 100% turbine and balance of plant availability.
You must insert an Hourly Profile, do so to the right by completing VI(a)(i). Table Part VI (a) below will be populated automatically from your data entered in Part V(a)(i), creating the project's 12 x 24 annual energy production inclusive of wake losses, suboptimal performance, environmental losses, and electrical losses. Downtime associated with O&M including planned or unplanned maintenance is not included and will be covered by Part VI (b) and Part VI (c) below.
|  | Legend | [31 empty] | Check: | 8,760 Hourly Values Missing
|  |  | Grey cell is automatically calculated | [27 empty] | Table VI(a) is incomplete, please enter all hourly profiles in VI (a) (i) >>> | JANUARY
White cell is to be updated by the WEA Leaseholder
|  | 0 | If sheet is filled out correctly, value to the immediate left should be zero | [29 empty] | HE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | Month
|  |  | Pre-populated | [12 empty] | HE | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 0 | [35 empty] | Avg | 0
1 | bar: HE to Dec
|  | Complete the fields below | [13 empty] | HE: 2 |  |  |  |  | 2
|  | Eligible Facility Location |  | Latitude | [11 empty] | HE: 3 |  |  |  |  | 3
|  |  |  | Longitude | [11 empty] | HE: 4 |  |  |  |  | 4
|  | Turbine capacity |  | MW | [11 empty] | HE: 5 |  |  |  |  | 5
|  | Number of turbines |  | # | [11 empty] | HE: 6 |  |  |  |  | 6
|  | Hub height |  | m | [11 empty] | HE: 7 |  |  |  |  | 7
[16 empty] | HE: 8 |  |  |  |  | 8
|  | Annual average wind speed at hub height across turbine locations | [13 empty] | HE: 9 |  |  |  |  | 9
|  |  |  | m/s | [11 empty] | HE: 10 |  |  |  |  | 10
[16 empty] | HE: 11 |  |  |  |  | 11
|  | Gross energy (annual 30-year average) | #DIV/0! | MWh/year | [11 empty] | HE: 12 |  |  |  |  | 12
[16 empty] | HE: 13 |  |  |  |  | 13
|  | Annual average losses | [13 empty] | HE: 14 |  |  |  |  | 14
|  | Internal wake losses | #DIV/0! | [12 empty] | HE: 15 |  |  |  |  | 15
|  | External wake losses | #DIV/0! | [12 empty] | HE: 16 |  |  |  |  | 16
|  | Suboptimal performance losses | #DIV/0! | [12 empty] | HE: 17 |  |  |  |  | 17
|  | Environmental losses | #DIV/0! | [12 empty] | HE: 18 |  |  |  |  | 18
|  | Electrical losses to POI | #DIV/0! | [12 empty] | HE: 19 |  |  |  |  | 19
|  | Project downtime - planned | #DIV/0! | [12 empty] | HE: 20 |  |  |  |  | 20
|  | Turbine downtime - unplanned | 100% | [12 empty] | HE: 21 |  |  |  |  | 21
|  | Balance of plant downtime - unplanned | 100% | [12 empty] | HE: 22 |  |  |  |  | 22
[16 empty] | HE: 23 |  |  |  |  | 23
|  | P50 Net energy (annual 30-year average) | #DIV/0! | MWh/year | [11 empty] | HE: 24 |  |  |  |  | 24
|  | P50 Net capacity factor | #DIV/0!
|  | 1-year P99 Net energy |  | GWh/year
1-year P99 Net capacity factor
[15 empty] | Duke OSW ARFI Submission Uptake Form - Version FINAL 01/29/2025 | [16 empty] | FEBRUARY
|  | Column ID | (i) | (ii) | (iii) | (iv) | (v) | (vi) | (vii) | (viii) | (ix) | (x) | (xi) |  | Part VI (b)
|  |  | Gross annual energy (MWh) | Internal wake loss (%) | External wake loss (%) | Suboptimal performance loss (%) | Environmental loss (%) | Electrical losses (%) | Gross Annual Energy minus (i)-(vi) losses (MWh) | Project downtime - planned (%) | Turbine downtime - unplanned (%) | Balance of plant downtime - unplanned (%) | Net annual energy (MWh) |  | Operational Information - PLANNED Maintenance Profile | [17 empty] | HE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 |  |  | Month
|  | P50 Annual Estimates | [12 empty] | Monthly Adjustment Factors as Percentage of Expected Production | [49 empty] | Avg
|  | Year | [30 empty] | 1
|  | 1 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | HE: Table VI(b) and VI(c) request information related to the maintenance requirements of the Project. There are two tables. The first, VI (b), requests the maintenance profile for PLANNED activities associated with both the turbines and all balance of plant. This would include all pre-scheduled maintence, inspections, tests, component and consumables replacement. VI( c) (below) requests the annual expectations for UNPLANNED activities for both the turbines and all balance of plant. The downtime estimates year to year are expected to be derived based on the experience of the developer and experience with the proposed technology. |  |  |  |  | 2
|  | 2 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! | [19 empty] | 3
|  | 3 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! | [19 empty] | 4
|  | 4 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! | [19 empty] | 5
|  | 5 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! | [19 empty] | 6
|  | 6 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! | [19 empty] | 7
|  | 7 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! | [19 empty] | 8
|  | 8 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! | [19 empty] | 9
|  | 9 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! | [19 empty] | 10
|  | 10 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | HE: Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) |  |  |  |  | 11
|  | 11 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Year | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |  |  |  | 12
|  | 12 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! | [19 empty] | 13 | bar: Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year
|  | 13 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 2 |  |  |  |  | 14
|  | 14 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 3 |  |  |  |  | 15
|  | 15 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 4 |  |  |  |  | 16
|  | 16 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 5 |  |  |  |  | 17
|  | 17 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 6 |  |  |  |  | 18
|  | 18 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 7 |  |  |  |  | 19
|  | 19 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 8 |  |  |  |  | 20
|  | 20 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 9 |  |  |  |  | 21
|  | 21 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 10 |  |  |  |  | 22
|  | 22 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 11 |  |  |  |  | 23
|  | 23 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 12 |  |  |  |  | 24
|  | 24 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 13
|  | 25 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 14
|  | 26 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 15
|  | 27 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 16 |  |  |  | MARCH
|  | 28 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 17
|  | 29 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 18 |  |  |  |  | HE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | Month
|  | 30 | [6 empty] | 0 | #DIV/0! | 100% | 100% | #DIV/0! |  |  | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 19 | [36 empty] | Avg
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 20 |  |  |  |  | 1
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 21 |  |  |  |  | 2
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 22 |  |  |  |  | 3
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 23 |  |  |  |  | 4
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 24 |  | Table is Incomplete. Information may be Required. <<< |  |  | 5
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 25 |  |  |  |  | 6
Continued Right >>>> | [15 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 26 |  |  |  |  | 7
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 27 |  |  |  |  | 8
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 28 |  |  |  |  | 9
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 29 |  |  |  |  | 10
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 30 | 0 |  |  |  | 11
12
13
14
[15 empty] | Duke OSW ARFI Submission Uptake Form - Version FINAL 01/29/2025 | [17 empty] | 15
[15 empty] | Part VI (c) | [17 empty] | 16
[15 empty] | UNPLANNED Maintenance - Production Adjustment Assumptions | [17 empty] | 17
18
19
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) |  |  |  |  | 20
21
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: Year; Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Jan: Turbine ramp up downtime; Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Feb: Balance of plant ramp up downtime; Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Mar: Turbine downtime - all other; Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Apr: Balance of plant downtime - all other |  |  |  |  | 22
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: Year |  |  |  |  | 23
24 | bar: Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year
2
3
4
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 5 |  |  |  | APRIL
6
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 7 |  |  |  |  | HE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  | Month
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 8 | [36 empty] | Avg
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 9 |  |  |  |  | 1
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 10 |  |  |  |  | 2
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 11 |  |  |  |  | 3
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 12 |  |  |  |  | 4
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 13 |  |  |  |  | 5
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 14 |  |  |  |  | 6
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 15 |  |  |  |  | 7
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 16 |  |  |  |  | 8
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 17 |  |  |  |  | 9
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 18 |  |  |  |  | 10
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 19 |  |  |  |  | 11
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 20 |  |  |  |  | 12
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 21 |  |  |  |  | 13
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 22 |  |  |  |  | 14
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 23 |  |  |  |  | 15
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 24 |  | Table is Incomplete. Information may be Required. <<< |  |  | 16
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 25 |  |  |  |  | 17
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 26 |  |  |  |  | 18
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 27 |  |  |  |  | 19
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 28 |  |  |  |  | 20
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 29 |  |  |  |  | 21
[16 empty] | Note: Enter factors in decimal format, where 1 equals no adjustment (i.e. a decrease of 2% should be entered as 0.98) Year: 30 | 0 |  |  |  | 22
23
24
Continued Right >>>>
MAY
[33 empty] | HE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | Month
Avg
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
JUNE
[33 empty] | HE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  | Month
Avg
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
JULY
[33 empty] | HE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | Month
Avg
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
AUGUST
[33 empty] | HE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | Month
Avg
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
SEPTEMBER
[33 empty] | HE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  | Month
Avg
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
OCTOBER
[33 empty] | HE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | Month
Avg
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
NOVEMBER
[33 empty] | HE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 |  | Month
Avg
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
DECEMBER
[33 empty] | HE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | Month
Avg
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
END
This Production Date Form is a portion of the requirements of Sections 8.B.vii of the Acquisition Request for Information (ARFI). These minimum data requirements must be completed in this Form and submitted in addition to any required narrative outlined in the above referenced Sections of the ARFI. Following the legend below, please complete the fields directly below and tables in Part VI (a) (i): Representative Deliveries in Representative Year (far right), and Part VI (b) and Part VI (c): Operational Data Adjustments for Planned and Unplanned Maintenance, respectively, in the center of this Form.